## Slide 1: HOSS online event 4 February 2021 Developing a UK VI Specialist VI Curriculum Framework Project update Linda James, Rory Cobb and Sue Keil

## Slide 2
Background and brief overview of the project
Project methodology
Consultation update
Resources hub update
Australia ECC project
Next steps

## Slide 3: Project background and overview

## Slide 4: VIEW Specialist VI Curriculum discussion paper (2018)
A range of outcomes and frameworks for learners with VI in the UK; BUT
  No consensus on which to use or how to use them
  Lack of consistency and coherence
  Lack of a shared vocabulary
Better long term outcomes for young people with VI with independent learning, living, mobility and social communication skills; BUT
  Demands of mainstream academic curriculum take priority – over-emphasis on ‘access to learning’ vs ‘learning to access’
Notes: So, reflecting on all of this, Rory and I started writing a discussion paper on behalf of VIEW. With a great deal of input from Mike, Graeme and Rachel from VICTAR, in particular, the paper explored the issues that Rory and I have been discussing. This led to the conclusion that we need a new model for specialist intervention in the UK which provides a single, unifying framework and that incorporates existing curricula / frameworks such as the NatSIP Learner Outcomes, and the habilitation and early years outcomes from the Hab Quality Standards and the DJVI
The ‘Access to learning / learning to access’ model would provide the conceptual framework – i.e. the underpinning philosophy.
When this idea was presented to the VI education sector, it received a very positive response. We also discovered that many VI services and VI special and resourced schools have developed their own resources and approaches to teaching the specialist VI curriculum. Consequently, the project partnership was set up, a project plan developed, and thanks to Caireen who was able to obtain funding through RNIB, the project is about to begin.

## Slide 5
Providing ‘Access to Learning’
Teaching ‘Learning to Access’

## Slide 6: Specialist VI curriculum framework project
Joint RNIB/VIEW\VICTAR, UOB/TPT 2-year project with the aims of developing:
A nationally recognised, UK specialist VI curriculum framework providing a new model for specialist intervention in the UK
Single, unifying framework incorporating existing curricula / frameworks
‘Access to learning / learning to access’ to provide the conceptual basis

## Slide 7: Project structure
2 strands:
A UK specialist VI curriculum framework which will clarify and define the elements of specialist skill development, interventions and best practice support that are essential for children and young people with vision impairment
A resource hub containing or signposting to a wide range of resources that support the specialist VI curriculum, made available through a single online platform hosted by RNIB BookShare

## Slide 8: Project management and implementation
Management committee
  Representatives from RNIB, VIEW, VICTAR (UOB), and TPT
Project manager
Specialist QTVI advisor
VIEW consultants
VICTAR (UOB) consultants
Reference group
  Representatives from key stakeholder organisations/groups from across the UK

## Slide 9: Project methodology

## Slide 10: Strand 1: Developing a UK Specialist VI Curriculum Framework
Led by VICTAR and RNIB
UK-wide consultation
Drawing upon experts across the VI education sector, representing different roles and types of expertise
Applying ‘The Delphi Method’ (as used by Emerson and Corn, 2006 and Corn and Koenig, 2002)
  A method used to form a consensus on a complex topic.
  Uses a group of participants (‘panellists’) selected for their expertise on the topic
  Conducted over a number of rounds: idea generation stage > refining over time

## Slide 11: Strand 2: Developing an online resource hub
Led by VIEW and RNIB:
VI services, schools and others that have developed VI curriculum resources to share these with the VIEW / RNIB project team
Interim classification scheme devised for categorising the curriculum resources
Each resource ‘matched’ to the area of expertise of VI professionals (QTVIs, RQHSs) who will act as ‘critical friends’ / reviewers
Resource providers to be paired with resource reviewers
Training for reviewers, protocols and permissions to be obtained
Resources uploaded to (or signposted via) RNIB BookShare to enable them to be freely shared amongst VI education professionals

## Slide 12: Delphi consultation update
Stage 1 of consultation to commence in February
Anticipated that we will run seven focus groups in total
  five groups for professionals (n=35)
  one group for course leads running professional training courses (n=6)
  one group for parents/young people representatives (n=8)
Rigorous process followed to identify representatives for the panel, ensuring good representation across the UK which is reflective of the range of professionals working with children and young people with vision impairment, and their caseloads

## Slide 13: Resources hub update
24 offers from VI services, schools and organisations to provide resources
Further information about resources for categorising, and permissions for sharing, being obtained
65 offers from VI professionals to act as reviewers
  Reviewer meetings with project QTVI late February 2021
Reviewers and providers to be matched and introduced

## Slide 14: Australia expanded core curriculum (ECC) project

## Slide 15: Australia ECC project
Joint project – University of Southern Queensland (lead) Vision Australia (sponsor), SPEVI (supporting role)
Similar problems to UK – ECC considered ‘extra’ to mainstream school curriculum
Concerns about poor employment outcomes for YP with VI
Developing a series of nationally accredited vocational education and training (VET) courses in ECC subjects
  Aimed at VI students in last 4 years of mainstream secondary school
  Delivered online in same way as standard VET courses
  Will be approved by national regulator – Australia Skills Quality Authority (ASQA)
Courses to be trialled in 2021
Our two project teams to remain in contact, provide regular updates

## Slide 16: Next steps
Identifying further resources
  If you have any resources you would like to share, please email: specialistvicurriculum@gmail.com
Continuing with the Delphi consultation to agree the UK specialist VI curriculum framework
  Planned completion date October 2021
Review resources and upload to RNIB BookShare hub
  Planned completion date November 2021

## Slide 17: For further information: Web: Specialist VI Curriculum framework - VIEW (viewweb.org.uk) Email: specialistvicurriculum@gmail.com

## Slide 18: References
Corn, A. L., & Koenig, A. J. (2002). Literacy for students with low vision: A framework for delivering instruction. Journal of Visual Impairment & Blindness, 96(5), 305-321.
Emerson, R. S. W., & Corn, A. L. (2006). Orientation and mobility content for children and youths: A Delphi approach pilot study. Journal of Visual Impairment & Blindness, 100(6), 331-342
  McLinden M, Douglas G, Cobb R, Hewett R and Ravenscroft J (2016) ‘Access to learning’ and ‘learning to access’: Analysing the distinctive role of specialist teachers of children and young people with vision impairments in facilitating curriculum access through an ecological systems theory’. British Journal of Visual Impairment 2016, Vol. 34(2) 179–197
  Keil S and Cobb R (2019) Learning to Access: why we need a new UK specialist curriculum to enable equitable participation in education for children and young people with vision impairment. VIEW discussion paper. https://viewweb.org.uk/specialistcurriculum/
  VIEW Teach (May, 2019) ‘The importance of specialist outcomes for learners with vision impairment ’VIEW Teach. The journal of the education vision impairment workforce. Summer term, issue 1, May 2, 2019 https://viewweb.org.uk/view-journal/